## RFIs
Rfi # | Subject | Ball In Court | Date Initiated | Due Date | Overdue | Due Date Variance | Status
1 | Warehouse and Penthouse Finishes |  | 2026-01-20 | 2026-01-23 | No | 3 | Closed
2 | Penthouse Slab Loadings (Icon RFI-004) |  | 2026-01-21 | 2026-01-26 | No | 8 | Closed
3 | Air Valve Installation Method (Icon RFI-002) |  | 2026-01-21 | 2026-01-26 | No | 9 | Closed
4 | Stilmas – Utility Request Form |  | 2026-01-26 | 2026-01-30 | No | 0 | Closed
5 | Floor flatness verification at MECART |  | 2026-01-27 | 2026-01-30 | No | -3 | Closed
6 | Icon Industrial Constructability Review |  | 2026-01-28 | 2026-02-11 | No | 1 | Closed
7 | Controlled Temperature Room Clarification |  | 2026-01-28 | 2026-02-04 | No | 6 | Closed
8 | Canem Constructability Review (Canem RFI-001) |  | 2026-01-28 | 2026-02-02 | No | 7 | Closed
9 | Constructability Review (18DEC2025) Close Out |  | 2026-01-28 | 2026-02-04 | No | 21 | Closed
10 | Penthouse Housekeeping Pad Layout Clarifications |  | 2026-01-28 | 2026-02-04 | No | 36 | Closed
11 | Ut-201 Mechanical Penthouse EF4 Epoxy at Housekeeping Pads |  | 2026-01-29 | 2026-02-04 | No | 0 | Closed
12 | Mecart Wall System Penetrations (ICON RFI-006) |  | 2026-01-29 | 2026-02-03 | No | 10 | Closed
19 | Tubing Wall Thickness (ICON RFI-001) |  | 2026-02-10 | 2026-02-17 | No | 0 | Closed
20 | Air Flow Values (ICON RFI-003) |  | 2026-02-10 | 2026-02-17 | No | 0 | Closed
13 | "Moveable Partition Manufacture” Clarifications |  | 2026-02-04 | 2026-02-11 | No | -1 | Closed
14 | Safety Swing Door Clarification |  | 2026-02-04 | 2026-02-11 | No | -1 | Closed
15 | Furniture Details |  | 2026-02-04 | 2026-02-11 | No | -1 | Closed
16 | HAZOP Documentation |  | 2026-02-04 | 2026-06-01 | No | -102 | Closed
21 | Fire Hydrant Flow Test |  | 2026-02-10 | 2026-02-17 | No | 0 | Closed
18 | Painting of Mechanical and Electrical Components |  | 2026-02-06 | 2026-02-11 | No | -1 | Closed
22 | Clean Room Pressurization and Testing |  | 2026-02-11 | 2026-02-19 | No | 0 | Closed
23 | M & E Support from Metal Deck |  | 2026-02-12 | 2026-02-19 | No | 4 | Closed
24 | Review and Clarification of Wall Types and Heights |  | 2026-02-12 | 2026-02-19 | No | -2 | Closed
25 | Process Instrumentation Scope |  | 2026-02-12 | 2026-02-19 | No | -1 | Closed
26 | Electrical Room Underground Conduit Installations |  | 2026-02-13 | 2026-02-23 | No | 2 | Closed
27 | Access Control Clarifications |  | 2026-02-13 | 2026-02-23 | No | 1 | Closed
28 | Data Comms Constructability Review Questions |  | 2026-02-13 | 2026-02-23 | No | 9 | Closed
29 | Storage Racking Height |  | 2026-02-13 | 2026-02-23 | No | -6 | Closed
30 | Clock Type |  | 2026-02-13 | 2026-02-23 | No | 7 | Closed
32 | Foxfab Connection Box |  | 2026-02-19 | 2026-02-27 | No | 13 | Closed
33 | ASCO |  | 2026-02-19 | 2026-02-27 | No | 13 | Closed
34 | Chilled Water/Chilled Glycol insulation specification contradiction |  | 2026-02-24 | 2026-03-03 | No | 6 | Closed
35 | HEPA and Clean Room certification spec |  | 2026-02-26 | 2026-03-05 | No | 4 | Closed
36 | Main Electrical Room Proposed Change |  | 2026-03-03 | 2026-03-10 | No | 3 | Closed
37 | Process Instrumentation PLC and Hardware |  | 2026-03-04 | 2026-03-11 | No | 0 | Closed
38 | Building signage lighting requirements |  | 2026-03-04 | 2026-03-11 | No | 2 | Closed
39 | Missing exhaust stack support structure, Gridline D3 |  | 2026-03-11 | 2026-03-18 | No | -1 | Closed
40 | Ceiling Assembly Type and Height Confirmation – Micro Lab LB-101 |  | 2026-03-11 | 2026-03-16 | No | -3 | Closed
41 | Main Electrical Room Proposed Changes R1 |  | 2026-03-13 | 2026-03-18 | No | 1 | Closed
43 | Radon rock and membrane specifications |  | 2026-03-17 | 2026-03-21 | No | -2 | Closed
44 | Fillcrete for SOG backfill |  | 2026-03-17 | 2026-03-21 | No | -1 | Closed
45 | Penthouse Mechanical & Electrical Painting Exemption |  | 2026-03-17 | 2026-03-23 | No | -4 | Closed
17 | Fire Spray Requirement for Structure Supporting Penthouse Slab | Robbie Gray, Andre-Pierre Ghys, Bernard Gagnon, Tiffany Tjong | 2026-02-04 | 2026-02-11 | Yes | 40 | Open
31 | Steam Safety Relief Valves | Lesley Woods | 2026-02-17 | 2026-04-01 | No | -9 | Open
42 | Clarification on Required Concrete Removal per Drawing 2S01 | Andreas Loutas | 2026-03-16 | 2026-03-23 | No | 0 | Open
46 | Universal Washroom Device Adjustments | Trent Eklund | 2026-03-18 | 2026-03-25 | No | -2 | Open
47 | Duct Cleaning Requirements Clarification | Vincent Pisio, Dan Riske, Jonathan Garvey-Wong, Robbie Gray, Andre-Pierre Ghys, Vasyl Zaiets, Bernard Gagnon, Tiffany Tjong | 2026-03-18 | 2026-03-25 | No | -2 | Open